## Prod Readiness
PRODUCTION READINESS CHECKLIST
Demo-ready example statuses: assumed checks are marked Passed; HTTPS/TLS, patch management, and recovery testing are flagged Failed pending evidence. Update against the actual environment before production.
# | Validation item | Expected result | Status | Notes / evidence
1 | EC2 instance | Instance is running and in the intended region/type. | Passed | Assumed passed for the demo; confirm in EC2 console.
2 | Nginx service | Nginx service is active and enabled where required. | Passed | Assumed active for the demo; confirm with systemctl status nginx.
3 | SSH access | SSH is active and restricted to approved IPs/users. | Passed | Assumed restricted; confirm security-group source ranges and SSH settings.
4 | CPU & memory | CPU and memory usage are within acceptable limits. | Passed | Assumed normal for the demo; confirm CloudWatch/OS metrics.
5 | Browser validation | Website loads successfully over the intended protocol. | Passed | Assumed site loads; confirm by opening the deployed URL.
6 | Application logs | No unresolved critical errors appear in application or service logs. | Passed | Assumed clean for the demo; inspect app and Nginx logs.
7 | Backup | A recent snapshot/backup completed successfully and is retained. | Passed | Assumed snapshot completed; confirm snapshot state is Completed.
8 | Network configured | Only required inbound ports are exposed. | Passed | Assumed minimal inbound rules; review security group and firewall.
9 | Cost optimization | Instance size and supporting resources match current needs. | Passed | Assumed appropriately sized for the demo; review actual usage and billing.
10 | Unused resources | Unused volumes, IPs, snapshots, and other resources are removed or justified. | Passed | Assumed cleanup done; inspect for unattached/idle resources.
11 | HTTPS / TLS | HTTPS is enabled with a valid certificate and HTTP redirects to HTTPS where appropriate. | Failed | Treat as failed until HTTPS and certificate validity are confirmed.
12 | IAM permissions | Instance role and user permissions follow least privilege. | Passed | Assumed least privilege for the demo; review attached policies.
13 | Health checks | Application/service health checks are configured and passing. | Passed | Assumed healthy for the demo; confirm health-check results.
14 | Patch management | OS packages and application dependencies are patched to supported versions. | Failed | Treat as failed until pending security updates and dependency advisories are checked.
15 | Recovery test | A documented restore/recovery procedure has been tested successfully. | Failed | Treat as failed until a restore/recovery test is demonstrated.

## Summary
READINESS SUMMARY — DEMO STATUSES
Total checks
Passed
Failed
Not verified
Blocked
N/A
Important | These are illustrative demo statuses, not results from live infrastructure checks. Validate each item before treating the environment as production-ready.